## Basic Manual Gantt Chart
Task Name | Marks | Member | Start Date | End Date | Duration | Complete
Gantt Chart | 5 | Shourov | 2017-10-30 | 2017-11-03 | 4 | ✓
Research Client Base | 10 | Jiaming | 2017-10-30 | 2017-11-03 | 4 | ✓
Logo and Design | - | Max | 2017-10-30 | 2017-11-03 | 4 | ∫
Interview Potential Clients | 10 | Shourov | 2017-10-30 | 2017-11-05 | 6 | ✓
Feasibility Study | 10 | Jack | 2017-10-30 | 2017-11-12 | 13 | ∫
Initial Rights Research | 10 | Jack | 2017-12-04 | 2017-12-11 | 7 | ×
Context Diagram AND Data Flow Diagram | 10 | Max | 2017-11-06 | 2017-11-12 | 6 | ✓
System Flow Chart | 5 | Jack | 2017-11-13 | 2017-11-18 | 5 | ∫
Structure Chart | 10 | Shourov | 2017-11-19 | 2017-11-29 | 10 | ∫
IPO Chart | 10 | Shourov | 2017-11-23 | 2017-11-29 | 6
Data structures | 15 | Jack | 2017-11-25 | 2017-12-04 | 9
Algorithms | 20 | Everyone | 2017-12-04 | 2018-01-31 | 58
Screen Design | 15 | Max | 2017-11-06 | 2018-01-31 | 86
Internal Documentation | 15 | Everyone
Develop Test Data | 10 | Jiaming
Evaluate the Final Solution | 10 | Max
|  |  | Complete | half done | not started
|  |  | ✓ | ∫ | ×
Formulas:
End Date = [Start Date]+7

## TTPI
| - x axis | -data 1 | data 2
Task | Start | Start on day | Duration | End
max | 2016-02-01 | 0 | 43 | 2016-03-15
jiaming | 2016-02-03 | 2 | 211 | 2016-09-01
jack | 2016-03-01 | 29 | 275 | 2016-12-01
shouvo | 2016-03-15 | 43 | 5 | 2016-03-20
vu | 2016-09-01 | 213 | 110 | 2016-12-20
uv | 2016-12-01 | 304 | 20 | 2016-12-21