## Basic Manual Gantt Chart
Task Name | Marks | Member | Start Date | End Date | Duration | Complete
Gantt Chart | 5 | Shourov | 2017-10-23 | 2017-10-29 | 6
Research Client Base | 10 | Jiaming | 2017-10-23 | 2017-10-29 | 6
Logo and Design | - | Max | 2017-10-23 | 2017-10-26 | 3
Interview Potential Clients | 10 |  | 2017-10-30 | 2017-11-05 | 6
Feasibility Study | 10 |  | 2017-10-30 | 2017-11-12 | 13
Initial Rights Research | 10 |  | 2017-10-30 | 2017-11-05 | 6
Context Diagram AND Data Flow Diagram | 10 | Jiaming | 2017-11-06 | 2017-11-23 | 17
System Flow Chart | 5 | Jiaming | 2017-11-06 | 2017-11-23 | 17
Structure Chart | 10 |  | 2017-11-06 | 2017-11-23 | 17
IPO Chart | 10 |  | 2017-11-06 | 2017-11-23 | 17
Data structures | 15
Algorithms | 20 | Jack
Screen Design | 15 | Max
Internal Documentation | 10 | Everyone
Develop Test Data |  | Max
Evaluate the Final Solution |  | Max

## TTPI
| - x axis | -data 1 | data 2
Task | Start | Start on day | Duration | End
max | 2016-02-01 | 0 | 43 | 2016-03-15
jiaming | 2016-02-03 | 2 | 211 | 2016-09-01
jack | 2016-03-01 | 29 | 275 | 2016-12-01
shouvo | 2016-03-15 | 43 | 5 | 2016-03-20
vu | 2016-09-01 | 213 | 110 | 2016-12-20
uv | 2016-12-01 | 304 | 20 | 2016-12-21